## Masonry & Building
CHEVAL CLUB — MASONRY & BUILDING ITEMS TRACKER
1426 N. Orleans Street, Chicago, IL · Masonry repairs (Ready Home / Kipcon) · Updated June 22, 2026 — reflects HDG report dated 6/18/2026
# | Item / Location | Observed Condition | Status | Board Position / Interpretation | Proposed Remedy | Notes / Open Questions
1 | Through-wall flashing — copings | Limestone copings were not lifted to install new through-wall flashing as specified. | Confirmed Defect | HDG confirms copings were not raised and no through-wall flashing was installed, with no credit. The Board treats this as specified work paid for but not performed. | Lift copings; install new through-wall flashing per spec; credit or complete. | Base flashing stops short of the coping bed joint; porous CMU takes on water.
2 | Through-wall flashing — balustrades/columns | Decorative limestone columns/balustrades were not raised to install through-wall flashing. | Confirmed Defect | HDG confirms the balustrades/decorative columns were not lifted and no flashing installed, no credit. Board position: undelivered scope. | Lift balustrades; install through-wall flashing; credit or complete. | New base flashing extended up past the balustrade bed joint, blocking weeping.
3 | Sixth-floor window lintels | Sixth-floor window lintels were not removed and replaced as specified. | Confirmed Defect | HDG confirms lintels were not replaced and no credit was provided. Board position: paid-for scope not performed. | Replace lintels per spec; provide credit if not performed. | Also confirm whether new through-wall flashing above sixth-floor windows was installed (HDG: “was this completed?”).
4 | Tuckpointing — extent | Only spot-pointing performed; HDG found roof-side and exterior required 100% pointing. | Confirmed Defect | The Board contends the tuckpointing scope was under-performed; areas needing full pointing were only spot-pointed, and no water repellent was specified. | 100% tuckpoint where required; apply water repellent; reconcile cost. | Who defined the spot-pointing areas? Bricks shifting despite spot-pointing.
5 | East parapet — condition | Roof-side masonry in poor condition with efflorescence; should have been tuckpointed. | Open | The Board views the parapet condition as evidence of incomplete masonry work and an ongoing water path at the roof termination. | Tuckpoint/repair parapet; confirm flashing integration with the roof. | Photos 7, 24. Coordinate with roof base-flashing terminations.
6 | Exterior brick — movement | Brick on the exterior side moving outward; south-facing brick over the sixth-floor balcony shows efflorescence and washed-out mortar. | Open | The Board wants the cause of brick movement and mortar deterioration assessed; it may indicate water/structural issues beyond the contracted scope. | Structural/masonry assessment; repair as findings dictate. | Photos 28, 29. Determine if within or beyond the original scope.
7 | Sixth-floor balcony railing | Steel balcony railing embedded in the brick has expanded and cracked the adjacent brick and mortar. | Open | The Board treats the embedded-rail corrosion/expansion as a masonry repair item to be scoped and addressed. | Address corroded embedded steel; repair cracked brick/mortar. | Photo 30. Confirm whether in original scope.
8 | Unit 501 — balcony wall (south) | Water source at the 501 balcony wall, south exposure; inspection needed. | Open | If the source is masonry rather than roof, the Board considers it part of the masonry scope to identify and repair. | Inspect and identify source; if masonry, scope and remedy. | Cross-referenced from the roof tracker.
9 | Masonry contract — documentation | Change orders, inspection records, and close-out documents for the masonry contract. | Confirmed Defect | As with the roof, HDG found no change orders and no engineer punch lists/reports. The Board wants a complete written record before any final masonry payment. | Demand all masonry change orders, inspection reports, warranties, and close-out documents. | Final masonry balance ($9,373) outstanding — treat as subject to completion.
Status key:
Confirmed Defect
Open
In Progress
Monitoring
Awaiting Vendor
Resolved
“Confirmed Defect” = independently confirmed in the HDG report dated 6/18/2026. Working internal tracker; Board positions are interpretations for discussion with HDG and counsel. Not legal advice.