## Roof Punch List
CHEVAL CLUB — ROOF PUNCH LIST TRACKER
1426 N. Orleans Street, Chicago, IL · Roof replacement (Ready Home / Kipcon) · Updated June 22, 2026 — reflects HDG report dated 6/18/2026
# | Item / Location | Observed Condition | Status | Board Position / Interpretation | Proposed Remedy | Notes / Open Questions
1 | Original roof not removed (tear-off) | Existing modified-bitumen roof left in place; water found beneath it; concrete deck never exposed or inspected. | Confirmed Defect | HDG confirms the original roof was not removed as required and the contractor did not notify the owner or obtain approval. Spec and City permit both required a tear-off. The Board's position is this is a defect, not an authorized change. | Core to confirm layer count; assess deck condition; remediate to achieve a compliant, properly torn-off assembly. | Change order references “1st and 2nd layer of existing modified bitumen,” confirming layers left in place. Permit said tear-off.
2 | Insulation — one layer instead of two | Only one layer of insulation installed where two were required (mechanically fastened per contract). | Confirmed Defect | HDG confirms only one layer was installed, with no deduct change order or owner approval. The Board contends roughly half the specified insulation was delivered and a credit/remedy is owed. | HDG to verify installed depth/R-value; pursue full credit or remediation. | Ready Home refused the $8,000 ISO credit citing “up to two layers.” Reconcile depth figures (2.6″/layer vs 5.3″ min) against the executed spec.
3 | Membrane reduced to one ply | Two-ply system (base + cap) in the preliminary bid reduced to a single ply in the contract spec. | Open | The Board's position is the system's robustness was reduced and it is unclear whether the two-ply cost was credited; this should be reconciled and explained. | Confirm whether two-ply cost was included/credited; HDG to assess adequacy of single ply for this roof. | A spec change by the engineer; tie to the design/standard-of-care findings.
4 | Vapor retarder deleted | Vapor retarder required in the preliminary bid was deleted in the revised contract spec. | Open | Given the building's condensation history (no insulation above deck), the Board questions deleting the vapor retarder and whether its cost was removed from the price. | HDG to advise whether a vapor retarder is warranted; reconcile cost. | Condensation was the original problem; deletion is counter-intuitive and unexplained.
5 | Counterflashing & cant strips not installed | Cant strips at walls/curbs and compression counterflashing at flashed conditions were not installed. | Confirmed Defect | HDG confirms these were not installed. The Board views missing counterflashing/cant strips as a workmanship defect and water-entry risk. | Install cant strips and manufacturer-compliant counterflashing at all flashed conditions. | Termination bars not protected with counterflashing per manufacturer.
6 | Base flashing — debonding & terminations | Base flashings debonding/delaminating; terminations not appropriate at door sills, CMU/masonry walls, and penthouses; siding not removed to terminate. | Confirmed Defect | HDG confirms widespread base-flashing defects. The Board treats these as systemic installation failures, not isolated touch-ups. | Re-flash and properly terminate per manufacturer; remove siding where needed to terminate correctly. | Multiple photos (penthouses, west side, clerestory, door sills).
7 | 2″ drain & drain flashing (east area) | Drain not properly replaced/flashed; clamping ring found without bolts (no compression on the membrane); membrane improperly installed at drain. | Confirmed Defect | HDG states that had the membrane been properly installed at the drain, the backup would not have caused water intrusion — tying the east-side damage directly to workmanship. | Rebuild drain with proper sump, bolted clamping ring, and watertight membrane seal; verify line clear. | Root of the east-side damage. Ready Home credited $2,400 on drains — implicit acknowledgment.
8 | Drains not replaced (interior access) | Spec required replacing all drains (needs interior access and opening ceilings); does not appear to have occurred except failed east drains. | Open | The Board's position is the drain replacement scope was largely not performed and credits/remediation are owed. | Confirm which drains were actually replaced; price remaining scope or credit. | Only the two failed east drains were swapped after leaking.
9 | Open lap seams | Open seam laps found and recently patched by the installing contractor. | Monitoring | The Board views patched open laps as evidence of installation quality problems across the field, not a one-off. | HDG to assess seam integrity roof-wide; replace where compromised. | Contractor self-identified and patched on a recent review.
10 | Pourable sealer pockets | Piping in pourable sealer pockets not separated/primed before sealer placement. | Open | The Board treats improperly built pitch pockets as future leak points to be corrected. | Rebuild pockets per detail (separate/prime piping); or convert to proper detail. | Common future-failure point if left as-is.
11 | West roof — wet insulation (core) | Test cuts on the west side of the main roof found wet insulation. | Confirmed Defect | HDG confirms moisture within the new assembly and concludes the new roof is allowing water intrusion — i.e., a failure, not isolated to the east. | Core mapping to define wet extent; replace wet insulation/membrane as findings dictate. | Independent corroboration of the ~80% impedance reading.
12 | Walkway ponding (east–west) | Standing water/ponding on the walkway between the two roof sections. | Monitoring | The Board does not consider standing water acceptable on a new roof and links it to slope/drainage execution. | Confirm via ponding test; correct slope/drainage. | HOA ran a 48-hour test starting 4/20/2026 — capture results.
13 | Unit 601 / light well / interiors | Interior water infiltration (e.g., unit 601) and active dripping into a stairwell at a light well. | Open | The Board links interior leaks to roof/drain/flashing performance and treats them as part of the installation dispute. | Identify sources; reseal/re-flash; repair interior damage. | Interior damage supports resulting-damage (insurance) exposure.
14 | Stair & arched penthouse roofs | Loose/unadhered base flashing; gutters not removed and improperly flashed; coping reused, bent, too small, bowing; reused perimeter sheet metal; open gutter-to-edge. | Confirmed Defect | HDG confirms the penthouse roofs share the same flashing/gutter/coping defects. The Board treats these as defective installation and improper reuse of materials. | Re-flash, replace gutters/coping/sheet metal per spec and manufacturer. | Photos 13–22. Reuse of materials where replacement was warranted.
15 | Railings — wrong length / wood infills | New metal railings not the correct length; wood used to bridge gaps to the walls. | In Progress | The Board questions the altered layout and treats the railing work as not delivered as contracted. | Provide correct-length railings; remove wood infills; clarify layout change. | Ready Home credited $2,000 guardrails — confirms incomplete delivery.
16 | A/C condenser units | A/C units addressed in contract spec but not the preliminary spec; unclear if disconnected and freon recaptured. | Open | The Board wants confirmation the A/C work was done properly and when the cost was added. | Confirm proper disconnect/recapture and reconcile added cost. | Raised by HDG as an open question.
17 | Manufacturer warranty (GAF) | Only an expired 2011 GAF guarantee on record; no GAF record of the new (2025) assembly; HDG finds the roof not per manufacturer requirements. | Open | The Board paid for a warranted GAF system and is entitled to a valid, transferable warranty; HDG's findings suggest the assembly may not qualify as built. | HDG/contractor to secure a valid GAF warranty; confirm inspections; remediate to qualify. | Deck installed over most of the roof without clear final manufacturer inspection.
18 | Permit vs. as-built / code | Permit describes tear-off; work was a re-cover. HDG: the roof “does not meet code.” | Confirmed Defect | The Board's position is the installed work does not match the permitted scope and, per HDG, does not meet code — raising compliance and permit-validity issues. | HDG/counsel to assess; remediate to achieve code compliance. | Express permit issued 9/3/2025; address shown 1424 N. Orleans — confirm covers 1426.
19 | Documentation — change orders & reports | No written change orders; no drainage assessment report; no engineer site reports, interim or final punch lists; no shop-drawing review. | Confirmed Defect | HDG confirms the engineer produced none of the required reports/punch lists and did not meet the standard of care; the contract required all deviations to be authorized in writing. | Demand all missing documentation; preserve for HDG/counsel; pursue with both vendors' insurers via counsel. | Central to both the workmanship and professional-negligence (E&O) avenues.
Status key:
Confirmed Defect
Open
In Progress
Monitoring
Awaiting Vendor
Resolved
“Confirmed Defect” = independently confirmed in the HDG report dated 6/18/2026. Working internal tracker; Board positions are interpretations for discussion with HDG and counsel. Not legal advice.

## Financials
CHEVAL CLUB — ROOF PROJECT FINANCIALS
Proposed change order, credits, and balances — nothing signed or paid as of June 22, 2026
Category | Item | Amount | Status / Board Position | Notes
Contract balance | Final payment — roofing & deck install | 37412 | Disputed | “Subject to final completion and punch list approval,” which HDG's findings put in question (extensive non-completion).
Contract balance | Final payment — masonry | 9373 | Disputed | HDG found significant masonry scope not performed (through-wall flashing, lintels, full tuckpointing).
New charge (proposed) | Repair flooded roof area (to concrete; new ISO; disposal) | 23700 | Not authorized | Repairs damage HDG attributes to defective installation — defect correction, not a paid extra.
New charge (proposed) | Remove & reinstall ~⅓ of the floating deck | 16000 | Not authorized | Same damaged area; unsigned.
New charge (proposed) | Additional service hours / inspections (April 2026) | 18970 | Disputed / pressured | Offered at half if Board signs, or withdrawn if Association awards Ready Home the masonry project within 60 days with a deposit.
Credit (offered) | Tear-off credit (half of $10,207.45) | -5103.5 | Inadequate | HDG confirms tear-off to deck not performed — fuller credit arguable.
Credit (offered) | Concrete allowance credit (half of $7,500) | -3750 | Inadequate | Allowance unused — deck never exposed.
Credit (offered) | ISO board credit | 0 | Refused — contested | HDG confirms one layer where two required; refusal contested.
Credit (offered) | Drains credit | -2400 | Accepted by RHI | Credited in full — consistent with HDG drain findings.
Credit (offered) | Guardrails credit | -2000 | Accepted by RHI | Credited in full — confirms railings not properly delivered.
| Total new charges proposed | 58670
| Total credits offered | -13253.5
| Outstanding contract balances | 46785
| Net new exposure if change order signed as written | 92201.5
Nothing in this tab has been signed or paid. An unsigned change order is a proposal, not a debt. Figures to be confirmed against executed documents. Not legal or financial advice.